## ProjectTask1
Activity Description | Duration
Start of project | 0
Preparation of tender | 20
Evaluation of technical bid | 15
Evaluation of commercial bid | 7
Award of contract | 7
Ordering of equipment | 4
Site handling over | 7
Delivery of equipment | 60
Erection of civil structures | 20
Erection of mechanical equipment | 35
Erection of electrical equipment | 25
Testing of plant | 7
On load testing | 7
Commissioning | 1
End of project | 0

## ProjectTask2
ID | Task Name | Duration
1 | Define project objectives and describe mission statement | 2 days
2 | Ensure total participation by training team support staff | 4 days
3 | Create list of target departments | 1 day
4 | Perform departmental training needs analysis | 7 days
5 | Compile results and present findings to training coordinator | 2 days
6 | Prioritize training delivery according to critical need | 2 days
7 | Inform department heads of the training initiative | 2 days
8 | Determine if training can be done in-house or outsourced | 1.5 days
9 | Define vendor deliverables - can they meet our needs? | 1 day
10 | Obtain vendor commitment to training rollout schedule | 3 days
11 | Review and customize training material | 7 days
12 | Obtain approval for purchase orders to cover vendor invoices | 2 days
13 | Create a list of training recipients by department | 2 days
14 | Send skill assessment forms to department heads | 2 days
15 | Collect and compile results by department | 5 days
16 | Initiate end-user placement matrix | 3 days
17 | Finalize project budget | 2 days

## ProjectTask2Remaining
ID | Task Name | Duration
18 | Determine course dates, start and end times, and locations | 3 days
19 | Post course outlines and schedule on corporate intranet | 1 day
20 | Establish support through help desk for post-training questions | 1 day
21 | Reserve training rooms | 1 day
22 | Coordinate with information technology team for optimal workstation and equipment performance | 1 day
23 | Order training manuals and necessary material | 7 days
24 | Order promotional material | 7 days
25 | Create posters and place them in high-traffic areas | 4 days
26 | E-mail invitation to participants | 1 day
27 | Arrange for catering of meals and refreshments | 1 day
28 | Enroll users who registered via corporate intranet | 2 days
29 | Send out confirmations to these registration | 1 day
30 | Send out prework requirements | 2 days
31 | Monitor cancellations and late requests for training | 1 day
32 | In-house instructors | 1 day
33 | Outsourced instructors | 3 days
34 | Reuse or build an end-user course evaluation form (online or paper) | 2 days
35 | Reuse or build an special feedback form for instructors | 2 days
37 | Conduct training and track attendance | 10 days
38 | Collect feedback and compile results | 2.5 days
39 | Determine need for make up training | 1.5 days
40 | Update department heads with training results | 2 days
41 | Issue certificates of completion to participants | 1 day
43 | Discuss evaluations, results, and process improvements with training team support staff | 1 day
44 | Create a list of best practices and FAQ for future training endeavors | 3 days
45 | Discuss results with vendor for any improvements | 2 days
46 | Identify issues that were problems and improve them | 2 days
47 | Send ROI forms to participants and department heads | 2 days
48 | Measure ROI according to established parameters | 5 days
49 | Compile results and present findings to department heads and HR and training managers | 4 days
51 | Party!! For training team support staff (and vendor staff) | 1 day

## ProjectTask3Predecessor
ID | Activity Description | Duration | Predecessor
1 | Start of project | 0 days
2 | Phase-1
3 | Preparation of tender | 20 days | 1
4 | Evaluation of technical bid | 15 days | 3
5 | Evaluation of commercial bid | 7 days | 4
6 | Award of contract | 7 days | 5
7 | Phase-2
8 | Ordering of equipment | 4 days | 6
9 | Site handling over | 7 days | 6
10 | Delivery of equipment | 60 days | 8
11 | Erection of civil structures | 20 days | 9,10
12 | Erection of mechanical equipment | 35 days | 9,10
13 | Erection of electrical equipment | 25 days | 9,10
14 | Phase-3
15 | Testing of plant | 7 days | 11,12,13
16 | On load testing | 7 days | 15
17 | Commissioning | 1 day | 16
18 | End of project | 0 days | 17

## ProjectResource3
Resource Name | Type | Initials | Max. Units | Std. Rate
Material Manager (MM) | Work | MM | 100 | ₹ 550.00/day
Engineer (Er) | Work | Er | 300 | ₹ 500.00/day
Quality Controller (QC) | Work | QC | 200 | ₹ 550.00/day
Supervisor (Sr) | Work | Sr | 400 | ₹ 400.00/day
Office Assistant (OA) | Work | OA | 100 | ₹ 200.00/day
Electrician (EI) | Work | El | 100 | ₹ 250.00/day
Labors (LB) | Work | LB | 2000 | ₹ 100.00/day
Crane (C) | Work | C | 100 | ₹ 450.00/day
Excavator (EX) | Work | EX | 100 | ₹ 400.00/day
Cement (Cem) | Material | Cem |  | 400
Sand (S) | Material | S |  | 3000
Erection Tools (Ets) | Work | Ets | 200 | ₹ 100.00/day